## Summary
Name | Rajiv Dhakal, Md Hossain, Komal Gautam, Obioma Nduka
Month | Work hour | Total Hour | Month | Phase | Hour
2025-05-01 | 38 | 391 | 2025-05-01 | Built HTML form and dynamic table | 8
2025-06-01 | 80 |  | 2025-05-01 | Built HTML form, dynamic table and testing | 12
2025-07-01 | 68 |  | 2025-05-01 | Inited the project | 6
2025-08-01 | 111 |  | 2025-05-01 | Project structure | 12
2025-09-01 | 94 |  | 2025-06-01 | Backend Development | 50
|  |  | 2025-06-01 | Chart Integration | 30
|  |  | 2025-07-01 | Data Processing | 25
|  |  | 2025-07-01 | UI/UX Design | 43
|  |  | 2025-08-01 | Admin Tools | 23
|  |  | 2025-08-01 | Dynamic Behavior | 58
|  |  | 2025-08-01 | Testing & Debugging | 30
|  |  | 2025-09-01 | Admin Tools | 10
|  |  | 2025-09-02 | Documentation | 72
|  |  | 2025-09-03 | Testing & Debugging | 12
Formulas:
Month = [1]May!C4
Month = [1]June!C4

## May
Data Warehouse
Name | Rajiv Dhakal, Md Hossain, Komal Gautam, Obioma Nduka |  | Total Hour |  | Row Labels | Sum of Hour spent
Month | 2025-05-01 |  | 38 |  | Built HTML form and dynamic table | 8
Date | Day | Task Description | Phase | Hour spent | Built HTML form, dynamic table and testing | 12
2025-05-01 | Thursday |  |  |  | Inited the project | 6
2025-05-02 | Friday |  |  |  | Project structure | 12
2025-05-03 | Saturday |  |  |  | Grand Total | 38
2025-05-04 | Sunday
2025-05-05 | Monday
2025-05-06 | Tuesday
2025-05-07 | Wednesday
2025-05-08 | Thursday
2025-05-09 | Friday
2025-05-10 | Saturday
2025-05-11 | Sunday
2025-05-12 | Monday
2025-05-13 | Tuesday
2025-05-14 | Wednesday
2025-05-15 | Thursday
2025-05-16 | Friday
2025-05-17 | Saturday
2025-05-18 | Sunday
2025-05-19 | Monday | Create specification for the project | Inited the project | 6
2025-05-20 | Tuesday | Project setup, folder structure, FastAPI initialization | Project structure | 6
2025-05-21 | Wednesday | Project setup, folder structure, FastAPI initialization | Project structure | 6
2025-05-22 | Thursday
2025-05-23 | Friday
2025-05-24 | Saturday
2025-05-25 | Sunday
2025-05-26 | Monday
2025-05-27 | Tuesday | Sensor data form and table rendering | Built HTML form and dynamic table | 8
2025-05-28 | Wednesday | Sensor data form and table rendering | Built HTML form, dynamic table and testing | 6
2025-05-29 | Thursday | Sensor data form and table rendering | Built HTML form, dynamic table and testing | 6
2025-05-30 | Friday
2025-05-31 | Saturday
Formulas:
Name = [Name, row above]+1

## June
Data Warehouse
Name | Rajiv Dhakal, Md Hossain, Komal Gautam, Obioma Nduka |  | Total Hour |  | Row Labels | Sum of Hour spent
Month | 2025-06-01 |  | 80 |  | Backend Development | 50
Date | Day | Task Description | Phase | Hour spent | Chart Integration | 30
2025-06-01 | Sunday |  |  |  | Grand Total | 80
2025-06-02 | Monday | API design, Setup, create server, | Backend Development | 6
2025-06-03 | Tuesday | API design, Setup, create server, | Backend Development | 5
2025-06-04 | Wednesday | API design, Setup, create server, | Backend Development | 6
2025-06-05 | Thursday
2025-06-06 | Friday
2025-06-07 | Saturday
2025-06-08 | Sunday | video storage logic | Backend Development | 6
2025-06-09 | Monday | video storage logic, Test, Error solve | Backend Development | 4
2025-06-10 | Tuesday | video storage logic, Test, Error solve | Backend Development | 6
2025-06-11 | Wednesday | video storage logic, Test, Error solve | Backend Development | 5
2025-06-12 | Thursday
2025-06-13 | Friday | sensor data endpoints | Backend Development | 4
2025-06-14 | Saturday | sensor data endpoints, Test, Error solve | Backend Development | 5
2025-06-15 | Sunday | sensor data endpoints, Test, Error solve | Backend Development | 3
2025-06-16 | Monday
2025-06-17 | Tuesday
2025-06-18 | Wednesday | Chart.js setup for pie, bar, and line charts | Chart Integration | 4
2025-06-19 | Thursday | Chart.js setup for pie, bar, and line charts | Chart Integration | 4
2025-06-20 | Friday | Chart.js setup for pie, bar, and line charts | Chart Integration | 2
2025-06-21 | Saturday | Chart.js setup for pie, bar, and line charts | Chart Integration | 6
2025-06-22 | Sunday | Chart.js setup for pie, bar, and line charts | Chart Integration | 6
2025-06-23 | Monday
2025-06-24 | Tuesday
2025-06-25 | Wednesday | Chart.js setup for pie, bar, and line charts | Chart Integration | 4
2025-06-26 | Thursday | Chart.js setup for pie, bar, and line charts | Chart Integration | 4
2025-06-27 | Friday
2025-06-28 | Saturday
2025-06-29 | Sunday
2025-06-30 | Monday
2025-07-01 | Tuesday
Formulas:
Name = [Name, row above]+1

## Jul
Data Warehouse
Name | Rajiv Dhakal, Md Hossain, Komal Gautam, Obioma Nduka |  | Total Hour |  | Row Labels | Sum of Hour spent
Month | 2025-07-01 |  | 68 |  | Data Processing | 25
Date | Day | Task Description | Phase | Hour spent | UI/UX Design | 43
2025-07-01 | Tuesday |  |  |  | Grand Total | 68
2025-07-02 | Wednesday
2025-07-03 | Thursday
2025-07-04 | Friday
2025-07-05 | Saturday | File size categorization, sensor data aggregation, formatting | Data Processing | 5
2025-07-06 | Sunday | File size categorization, sensor data aggregation, formatting | Data Processing | 4
2025-07-07 | Monday | File size categorization, sensor data aggregation, formatting | Data Processing | 4
2025-07-08 | Tuesday
2025-07-09 | Wednesday | File size categorization, sensor data aggregation, formatting | Data Processing | 4
2025-07-10 | Thursday | File size categorization, sensor data aggregation, formatting | Data Processing | 6
2025-07-11 | Friday | File size categorization, sensor data aggregation, formatting | Data Processing | 2
2025-07-12 | Saturday
2025-07-13 | Sunday
2025-07-14 | Monday
2025-07-15 | Tuesday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 4
2025-07-16 | Wednesday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 5
2025-07-17 | Thursday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 4
2025-07-18 | Friday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 2
2025-07-19 | Saturday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 5
2025-07-20 | Sunday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 5
2025-07-21 | Monday
2025-07-22 | Tuesday
2025-07-23 | Wednesday
2025-07-24 | Thursday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 3
2025-07-25 | Friday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 3
2025-07-26 | Saturday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 6
2025-07-27 | Sunday | Layout structuring, responsive design, spacing, typography | UI/UX Design | 6
2025-07-28 | Monday
2025-07-29 | Tuesday
2025-07-30 | Wednesday
2025-07-31 | Thursday
Formulas:
Name = [Name, row above]+1

## Aug
Data Warehouse
Name | Rajiv Dhakal, Md Hossain, Komal Gautam, Obioma Nduka |  | Total Hour |  | Row Labels | Sum of Hour spent
Month | 2025-08-01 |  | 111 |  | Admin Tools | 23
Date | Day | Task Description | Phase | Hour spent | Dynamic Behavior | 58
2025-08-01 | Friday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 4 | Testing & Debugging | 30
2025-08-02 | Saturday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 7 | Grand Total | 111
2025-08-03 | Sunday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 7
2025-08-04 | Monday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 3
2025-08-05 | Tuesday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 2
2025-08-06 | Wednesday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 4
2025-08-07 | Thursday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 3
2025-08-08 | Friday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 5
2025-08-09 | Saturday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 7
2025-08-10 | Sunday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 7
2025-08-11 | Monday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 4
2025-08-12 | Tuesday | JavaScript for chart updates, dropdown logic, interactivity | Dynamic Behavior | 5
2025-08-13 | Wednesday
2025-08-14 | Thursday
2025-08-15 | Friday
2025-08-16 | Saturday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 6
2025-08-17 | Sunday | Dashboard controls, sensor selection, storage overview logic | Admin Tools | 5
2025-08-18 | Monday
2025-08-19 | Tuesday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 4
2025-08-20 | Wednesday | Dashboard controls, sensor selection, storage overview logic | Admin Tools | 4
2025-08-21 | Thursday
2025-08-22 | Friday | Dashboard controls, sensor selection, storage overview logic | Admin Tools | 5
2025-08-23 | Saturday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 7
2025-08-24 | Sunday
2025-08-25 | Monday
2025-08-26 | Tuesday | Dashboard controls, sensor selection, storage overview logic | Admin Tools | 5
2025-08-27 | Wednesday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 4
2025-08-28 | Thursday
2025-08-29 | Friday | Dashboard controls, sensor selection, storage overview logic | Admin Tools | 4
2025-08-30 | Saturday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 9
2025-08-31 | Sunday
Formulas:
Name = [Name, row above]+1

## Sept
Data Warehouse
Name | Rajiv Dhakal, Md Hossain, Komal Gautam, Obioma Nduka |  | Total Hour |  | Row Labels | Sum of Hour spent
Month | 2025-09-01 |  | 94 |  | Admin Tools | 10
Date | Day | Task Description | Phase | Hour spent | Documentation | 72
2025-09-01 | Monday | Final polish, code cleanup, user feedback loop | Admin Tools | 4 | Testing & Debugging | 12
2025-09-02 | Tuesday | Final report writing and documentation | Documentation | 12 | Grand Total | 94
2025-09-03 | Wednesday | Final report writing and documentation | Documentation | 12
2025-09-04 | Thursday | Final report writing and documentation | Documentation | 12
2025-09-05 | Friday | Final report writing and documentation | Documentation | 12
2025-09-06 | Saturday | Dashboard controls, sensor selection, storage overview logic | Admin Tools | 6
2025-09-07 | Sunday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 6
2025-09-08 | Monday | Cross-browser testing, layout fixes, performance tuning | Testing & Debugging | 6
2025-09-09 | Tuesday | Final report writing and documentation | Documentation | 12
2025-09-10 | Wednesday | Final report writing and documentation | Documentation | 12
2025-09-11 | Thursday
2025-09-12 | Friday
2025-09-13 | Saturday
2025-09-14 | Sunday
2025-09-15 | Monday
2025-09-16 | Tuesday
2025-09-17 | Wednesday
2025-09-18 | Thursday
2025-09-19 | Friday
2025-09-20 | Saturday
2025-09-21 | Sunday
2025-09-22 | Monday
2025-09-23 | Tuesday
2025-09-24 | Wednesday
2025-09-25 | Thursday
2025-09-26 | Friday
2025-09-27 | Saturday
2025-09-28 | Sunday
2025-09-29 | Monday
2025-09-30 | Tuesday
2025-10-01 | Wednesday
Formulas:
Name = [Name, row above]+1